## 工作表1
Validation schedule: 2022/02/14~2022/04/13.
Test item | Sample qty. | Report by lab. | Test duration | Status | 1st week | 2nd week | 3rd week | 4th week | 5th week | 6th week | 7th week | 8th week | 9th week | 10th week | 11th week | 12th week
[5 empty] | 1/27~2/2 | 2/3~2/9 | 2/10~2/16 | 2/17~2/23 | 2/24~3/2 | 3/3~3/9 | 3/10~3/16 | 3/17~3/23 | 3/24~3/30 | 3/31~4/6 | 4/7~4/13 | 4/14~4/20
BAT | 35 | WW | 2/8~2/18 | On-going |  | 2/8~2/25 @ WW
Non-Operational - Thermal Cycling - Deformation (Robustness) | 3 | IST | 2/25~3/17 | Not Start |  |  |  |  | 2/25~3/17 @ IST |  |  |  | DnP @IST
Non-operation - High Temperature/Humidity (STORAGE) - 85/85 | 4 | ATC | 2/25~3/18 | Not Start |  |  |  |  | 2/25~3/18 @ ATC
Non-Operational Cold & Hot Storage (-40/70°C) | 6 | ATC | 2/25~3/08 | Not Start |  |  |  |  | 2/25~3/08 @ ATC
Thermal profile (IR hot spots & thermo-couple temp measurements) | 2 | WW | 2/24~3/23 | Not Start |  |  |  |  | 2/24~3/23 @ WW
HALT | 9 | Chroma | 2/25~3/4 | Not Start |  |  |  |  | 2/25~3/4 @ Chroma
Four-corner voltage/temperature (Margin) | 3 | WW | 3/3~3/23 | Not Start | [5 empty] | 3/3~3/23 @ WW
Operational and non-operational Altitude tests - (Margin) | 3 | IST | 3/5~3/13 | Not Start | [5 empty] | 3/5~3/13 @ IST
Operation - High Temperature/Humidity w/AC power cycling (RDT/DMTBF) | 3 | WW | 2/21~4/5 | Not Start |  |  |  | 2/21~4/5 @ WW
Connector durability | 2 | WW | 3/10~3/23 | Not Start | [6 empty] | 3/10~3/23 @ WW
# Remark: * 1/29~2/6 -> Chinese New Year holidays. * 2/26~2/28 -> Holidays.(Peace Memorial Day) * 4/2~4/5 -> Holidays. (WomenDay, Children's Day and Tomb Sweepingcombined)
Chinse New Year
4/20 EV2 Exit
4/13 EV2 validation end day
2/14 EV2 validation start day
Today - 2/16